SpectrometerV2 Codebase Migration Plan

Incremental Migration from Current Codebase to Target Architecture

Project: SpectrometerV2

Revision: 1.2

Revision Date: July 16, 2026

Status: Controlled Engineering Document

# Revision History

| Revision | Date | Description | Author |
| --- | --- | --- | --- |
| 1.0 | July 2026 | Initial document. | Project Team |
| 1.1 | July 14, 2026 | Added Raspberry Pi as a first-class supported platform and updated platform, hardware abstraction, camera interface, testing, deployment, and migration requirements. | Project Team |
| 1.2 | July 16, 2026 | Added implementation-status annotations to migration phases, gates, and the first-sprint checklist, reflecting SpectrometerV2 Sprint 1 progress. Rebranded document project name to SpectrometerV2. | Project Team |

Implementation status (Rev 1.2): [Implemented] = built and verified in the SpectrometerV2 codebase; [In Progress] = partially implemented or scaffolding/interface in place; [Planned] = not yet started. Reflects branch sprint-1-skeleton as of July 16, 2026.

# 1. Migration Goal

Refactor the current codebase incrementally into a shared cross-platform architecture supporting Linux, Windows, and Raspberry Pi as first-class platforms without discarding proven scientific behavior.

# 2. Migration Rules

Preserve working behavior before refactoring.

Create golden test data before changing scientific algorithms.

Make small reversible changes.

Do not rewrite all platform code simultaneously.

Keep a working release branch and explicit rollback points.

# 3. Phase 0 — Baseline Preservation  [In Progress]

Tag the current working codebase.

Record supported workflows, dependencies, configuration values, camera behavior, and known limitations.

Capture representative raw images, spectra, calibration data, and outputs.

Preserve the existing synthetic test-data implementation, including multiple wavelengths, SNR, FWHM, and other currently supported parameters.

# 4. Phase 1 — Characterization and Golden Tests  [Planned]

Create regression fixtures from real and synthetic datasets.

Record expected peak wavelengths, amplitudes, FWHM, SNR behavior, calibration results, and output formats.

Use deterministic random seeds for synthetic regression data.

# 5. Phase 2 — Project Skeleton and Shared Services  [In Progress]

Create the new package structure without changing scientific results.

Introduce centralized configuration, logging, CLI parsing, error handling, and data models.

Maintain compatibility shims where needed.

# 6. Phase 3 — Extract Scientific Core  [Planned]

Move spectrum extraction, calibration, peak analysis, fitting, FWHM, SNR, and related algorithms into platform-neutral modules.

Verify each extraction step against golden outputs before removing legacy paths.

# 7. Phase 4 — Synthetic Spectrum Generator Migration  [Planned]

Identify and preserve every capability of the current synthetic-data implementation.

Move generation into a dedicated synthetic module.

Support multiple wavelengths, amplitude, FWHM, SNR, wavelength range, sampling, baseline, and deterministic random seed.

Route generated spectra through the standard analysis pipeline.

Do not remove the legacy generator until regression equivalence is demonstrated.

# 8. Phase 5 — Camera Abstraction  [In Progress]

Define a common camera contract.

Implement and validate USB camera adapters.

Implement Raspberry Pi-native camera adapters where compatible.

Keep vendor-specific and platform-specific APIs out of scientific-processing modules.

# 9. Phase 6 — Platform Migration  [Planned]

Linux: validate installation, camera discovery, acquisition, analysis, logging, persistence, and synthetic generation.

Windows: validate equivalent core functionality and supported camera paths.

Raspberry Pi: validate native and/or USB camera paths, performance constraints, headless operation where applicable, and scientific equivalence.

# 10. Phase 7 — GUI and Workflow Integration  [Planned]

Reconnect the user interface to the new application services.

Keep GUI code free of scientific algorithms.

Preserve familiar operator workflows where practical.

# 11. Phase 8 — Acceptance and Release  [Planned]

Run automated regression suites.

Run platform acceptance tests on Linux, Windows, and Raspberry Pi.

Verify real-camera and synthetic-data workflows.

Verify graceful failures and useful logs.

Document installation and platform-specific prerequisites.

# 12. Migration Gates

Gate A: Baseline captured and reproducible.  [In Progress]

Gate B: Configuration and logging operational.  [Implemented]

Gate C: Scientific core matches golden data.  [Planned]

Gate D: Synthetic generator matches preserved behavior and expanded requirements.  [Planned]

Gate E: Camera adapters satisfy the common contract.  [Planned]

Gate F: Linux, Windows, and Raspberry Pi acceptance tests pass.  [Planned]

Gate G: Legacy duplicated paths may be removed only after equivalence is demonstrated.  [Planned]

# 13. Principal Risks and Mitigations

Risk: Scientific behavior changes silently. Mitigation: golden datasets and numerical tolerances.

Risk: Raspberry Pi APIs contaminate the core architecture. Mitigation: strict adapter boundaries.

Risk: Platform camera behavior differs. Mitigation: capability discovery, metadata normalization, and hardware-in-the-loop tests.

Risk: Synthetic test generator loses existing features. Mitigation: preserve current implementation first and migrate feature by feature.

Risk: Large rewrite becomes untestable. Mitigation: incremental phases, release tags, rollback points, and migration gates.

# 14. Recommended First Implementation Sprint

1. Tag and archive the current working code.  [Implemented]

2. Inventory current features and hard-coded parameters.  [Planned]

3. Preserve representative real and synthetic datasets.  [Planned]

4. Establish the new package skeleton.  [Implemented]

5. Implement configuration validation and logging.  [Implemented]

6. Create the initial golden regression suite.  [Planned]

7. Begin extraction of the synthetic spectrum generator and scientific core.  [Planned]